## Slide 1: A Sample Sprint using Rally

## Slide 2: Agenda
First Day Planning
  Capacity and tasking
Standups
  Using the Tracking tab
Grooming
  Covering requirements and sizing
Demo and Retro

## Slide 3: High Level Sample Sprint
Week 1
Week 2
Week 3
Planning
Sprint 3
Grooming #1
Sprint 3
Grooming #2
Sprint 3
Grooming #3
Demo / Retro
15 minute standups each day
Rally updated before each stand up
Sprint 2

## Slide 4: Beginning of Sprint Planning
Held on the first day of the sprint
Review of sprint theme, velocity, any other sprint related news by Product Owner and Scrum Master
Each team member determines their capacity
Team decides who is working which stories in the sprint
Each team member enters tasks for each story in priority order, including an hour estimate of the task
During tasking, team asks Product Owner for additional clarification on stories if needed
Tasking continues until team reaches ~90% of their capacity.
If stories remain after team reaches capacity, they are moved into the backlog for future sprints

## Slide 5: Daily Stand-Up
Should be no longer than 15 minutes
Each team member gives an update with the following:
  What have you done since last stand up?
  What do you plan to do today?
  Are you blocked by anything?
If necessary, blockers are addressed by the Scrum Master outside of the stand-up
Always starts on time, in the same location regardless of attendees.
Rally is shown for sprint status and burndown.

## Slide 6: Grooming
Grooming for the next sprint is done while working the current sprint
Each story in the backlog for the next sprint is reviewed for clarity in priority order, ensuring the entire team is in agreement on requirements
Acceptance Criteria is refined
Stories are broken up into smaller stories if needed
Finally stories are given a relative size which reflects the amount of effort required (Fibonacci: 1,2,3,5,8,13,21,34)
Each grooming session should be no longer than 1 hour, to not take away from current sprint work, multiple sessions should be spread throughout the sprint

## Slide 7: Sizing Stories in Grooming
Sizing is the assignment of points to stories
Size has no correlation to hours
Teams gel in their sizing over several sprints, leading to consistency in their estimations
Effective grooming leads to predictable velocity, the average number of story points a team can usually fit into a sprint

## Slide 8: End of Sprint Review / Demo
Review work that has completed and not completed.
Work not completed is moved back into the backlog
Demonstrate work completed to the Stakeholders and Owners

## Slide 9: Retrospective
Facilitated by Scrum Master
Each team member answers two questions:
  What went well during the sprint?
  What needs to be improved for the next sprint?
Scrum Master takes suggestions and implements as necessary