## Slide 1: Scrum 101

## Slide 2: Agenda
Scrum Roles
Scrum Ceremonies and Concepts
Sample Sprint

## Slide 3: Scrum Roles

## Slide 4: Scrum Roles
Development Team
Product Owner
Scrum Master
Stakeholders

## Slide 5: Development Team
Usually a team of under 10 People
Cross Functional
  All Dev and QA in the same team
Ideally self-managing

## Slide 6: Product Owner
Voice of the customer
Represents Stakeholders
Writes Stories
Organizes and slots stories into iterations
Ideally one Product Owner per Scrum Team
Product Owners should not serve as Scrum Master

## Slide 7: Scrum Master
Ensures Scrum process is followed correctly
  Facilitates Grooming
  Oversees Stand-up meetings
  Runs Retrospectives
Enables teams to succeed by resolving blockers, allowing teams to focus on sprint work
Stands between Development team and any distractions

## Slide 8: Stakeholders
The Stakeholders are the customers.
Define the product
Enable the product to be developed.

## Slide 9: Scrum Ceremonies

## Slide 10: Ceremonies
Grooming
Planning (beginning of sprint kickoff)
Daily Stand-up
Demo (end of sprint review)
Retrospective

## Slide 11: Grooming
Grooming for the next sprint is done while working the current sprint
Each story in the backlog for the next sprint is reviewed for clarity in priority order, ensuring the entire team is in agreement on requirements
Acceptance Criteria is refined
Stories are broken up into smaller stories if needed
Finally stories are given a relative size which reflects the amount of effort required (Fibonacci: 1, 2, 3, 5, 8, 13, 21, 34)
Each grooming session should be no longer than 1 hour, to not take away from current sprint work, multiple sessions should be spread throughout the sprint

## Slide 12: Sizing Stories in Grooming
Sizing is the assignment of points to stories
Size has no correlation to hours
Teams gel in their sizing over several sprints, leading to consistency in their estimations
Effective grooming leads to predictable velocity, the average number of story points a team can usually fit into a sprint

## Slide 13: Beginning of Sprint Planning
Held on the first day of the sprint
Review of sprint theme, velocity, any other sprint related news by Product Owner and Scrum Master
Each team member determines their capacity
Team decides who is working which stories in the sprint
Each team member enters tasks for each story in priority order, including an hour estimate of the task
During tasking, team asks Product Owner for additional clarification on stories if needed
Tasking continues until team reaches ~90% of their capacity.
If stories remain after team reaches capacity, they are moved into the backlog for future sprints

## Slide 14: Daily Stand-Up
Should be no longer than 15 minutes
Each team member gives an update with the following:
  What have you done since last stand up?
  What do you plan to do today?
  Are you blocked by anything?
If necessary, blockers are addressed by the Scrum Master outside of the stand-up
Always starts on time, in the same location regardless of attendees.
Rally is shown for sprint status and burndown.

## Slide 15: End of Sprint Review / Demo
Review work that has completed and not completed.
Work not completed is moved back into the backlog
Demonstrate work completed to the Stakeholders and Owners

## Slide 16: Retrospective
Facilitated by Scrum Master
Each team member answers two questions:
  What went well during the sprint?
  What needs to be improved for the next sprint?
Scrum Master takes suggestions and implements as necessary

## Slide 17: High Level Sample Sprint
Week 1
Week 2
Week 3
Sprint 2
Planning
Sprint 3
Grooming #1
Sprint 3
Grooming #2
Sprint 3
Grooming #3
Demo / Retro
15 minute standups each day
Rally updated before each stand up